## GPG Action Plan
GENDER PAY GAP ACTION PLAN 2021-2022 |  | Key objectives: | [5 empty] | Weekly RAG | Interdependencies |  | Barriers to Delivery | Mitigations | Audit Committee | Quality Governance Committee | Performance & Finance Committee | Workforce Committee | Remuneration Committee | People Engagement Committee | Transformation Committee | Charitable Funds Committee | Trust Board |  |  |  | Weekly | Monthly | Bi-Monthly | Quarterly | Bi-Annually | Annually
Overall Ambition/vision: |  | Key Objective 1 : Branding/Communication/Transparency | [5 empty] | Green/Amber |  |  |  |  | Executive Leadership Team | Accountability Forum | Compliance and Risk Group | Health, Safety and Wellbeing Group | Safeguarding Group | Medical Devices Group | Infection, Prevention and Control Group | Information Governance Group | Data Quality and Security Group | External Provider Assurance Group | Organisational Resilience Group | Clinical Best Practice Group | Medicines Management Group | Patient Safety Group | Volunteer Advisory Forum | Patient Experience and Engagement Group | Planning and Performance Group | Operational Delivery Groups | Professional Standards Group | Education and Learning Group | Organisational Development and Staff Engagement Group | Equality, Diversity and Inclusion Group | Raising Concerns Forum | Workforce Planning and Delivery Group | Staff Partnership Forum | Quality CIP Delivery Group | QIA Sub-Group | Business and Partnerships Development Group | Products and Supplies Procurement Group | Capital Investment Group | Estates, Fleet and Make Ready Strategy Group | Transformation Programme Group | Digital Strategy Group | Sustainability Group
|  | Key Objective 2: Recruitment and Promotion processes/level of Satisfaction/ Data analysis | [5 empty] | Green/Amber
|  | Key Objective 3: Maternity/Paternity and Parental leave policies/Hybrid working | [5 empty] | Green/Amber
|  | Key Objective 4: Supporting Female Employees - Health, Wellbeing and retention | [5 empty] | Green/Amber
SRO | Bob Champion | Overall Workstream | [5 empty] | Green/Amber
Senior Management Support | Ali Lowe | Description of Engagement/Comm's to staff:
Committee Reported to: | Workforce Committee | Frequency of reporting: | Quarterly
Governance Group: | Equality, Diversity and Inclusion Group | Frequency of reporting: | Quarterly
Key Objective 1 : Branding/Communication/Transparency
Ref. | Objective/Deliverable | KPI (if relevant) | Reporting Period | Owner | Driven through Working Group/Task & Finish Group | Location of related action plans | Comments/Update: | Delivery Confidence | Evidence Provided of completion | Evidence Assurance Provided to Committee | [36 empty] | A
1.1 a | To ensure pictures on adverts and Annual reports on external website and Need to know are Male / Female balanced. | COMMS to ensure there is a balanced male & female representation & those from the 9 protected characteristics. Any images, pictures selected for adverts to be featured on external/internal website must show diversity. | • 30th October 2021 • 31st January 2022 • 30th April 2022 • 30th August 2022 • 31st December 2022 | Julie Hollings - Director of Communications and Engagement/ Rowena Welsford Associate Director of Workforce, Helen Adams Head of Resourcing (Job Adverts). | EDI group |  | Workforce gender split to be shown in IPR data. | Green/Amber
1.1 b | To increase the number females candidates/employees in Operations and Estates – as per staff data analysis 2020/ 2021 | Head of Recruitment to ensure jobs adverts are drafted to attract female candidates/employees by offering job share/flexible working where possible. | • 30th October 2021 • 31st January 2022 • 30th April 2022 • 30th August 2022 • 31st December 2022 | Paul Marshall Deputy Chief Operating Officer (Ambulance Operations Centres and Community Response), Bob Champion Director of WF, Rowena Welsford Associate Director of Workforce, Helen Adams Head of Resourcing, Nikki Irons Head of PTS. | EDI Group/AWE Network |  | Quarterly workforce analysis publication to show increase in female employees. | Green/Amber
1.2 | To ensure all EEAST Annual Reports are well balanced and show diversity in the selection of picture/photos in Gender. | Head of Governance & Comms to ensure all reports are male - female & all those from 9 protected characteristics, balanced e.g. age range, making reasonable adjustments for employees requiring equipment to carry out their role (where required). | • 30th October 2021 • 31st January 2022 • 30th April 2022 • 30th August 2022 • 31st December 2022 | Julie Hollings - Director of Communications and Engagement/Emma De Carteret Head of Governance. | EDI group |  | Workforce demographic data published in Annual Report. | Green/Amber
Key Objective 2: Recruitment and Promotion processes/level of Satisfaction/ Data analysis
Ref. | Objective/Deliverable | KPI (if relevant) | Due Date | Owner | Driven through Working Group/Task & Finish Group | Location of related action plans | Comments/Update: | Delivery Confidence | Evidence Provided of completion | Evidence Assurance Provided to Committee | [36 empty] | A
2.1 | To increase shortlisting of female candidates/employees in PTS, Air ops & Operations support & Estates | Job evaluation/ appraisals/Data analysis will show if there is progress | • 30th October 2021 • 31st January 2022 • 30th April 2022 • 30th August 2022 • 31st December 2022 | Rowena Welsford Associate Director of Workforce, Helen Adams Head of Resourcing Amy Antoni Deputy Head of Resourcing Barbara Shreeve/Caroline Nwadu/Emma Crawford AWE Chairs | EDI Group/EDI Team/AWE network |  | Recruitment equalities monitoring. | Green/Amber
2.2 | To increase shortlisting of female candidates/employees in Bands 6-Afc - Q14 NHS survey Organisation acts fairly: career progression | Job evaluation/ appraisals/Data analysis will show if there is progress. AWE networks to conduct a survey amongst female staff what prevents them for applying for promotion. | • 30th October 2021 • 31st January 2022 • 30th April 2022 • 30th August 2022 • 31st December 2022 | Rowena Welsford Associate Director of Workforce, Helen Adams Head of Resourcing Amy Antoni Deputy Head of Resourcing Barbara Shreeve/Caroline Nwadu/Emma Crawford AWE Chairs | EDI Group/EDI Team/AWE network |  | Workforce demographic data published in Annual Report. | Green/Amber
2.3 | To increase satisfaction in employees pay. (Suggest ways of encouraging internal promotion through applications of employees). (NHS Survey data suggests very low percentage are satisfied with their pay) | Job evaluation/ appraisals/Transparency of pay/ close Gender Pay gap | • 30th October 2021 • 31st January 2022 • 30th April 2022 • 30th August 2022 • 31st December 2022 | Bob Champion Interim Director of Workforce Sudha Pavanakumar Deputy Director of Workforce | EDI Group/EDI Team/AWE network |  | Annual national staff survey results. | Green/Amber
Key Objective 3: Maternity/Paternity and Parental leave policies/Hybrid working
Ref. | Objective/Deliverable | KPI (if relevant) | Due Date | Owner | Driven through Working Group/Task & Finish Group | Location of related action plans | Comments/Update: | Delivery Confidence | Evidence Provided of completion | Evidence Assurance Provided to Committee | [36 empty] | A
3.1 | To support Maternity & Paternity Requests fairly and equally and offer Hybrid working solutions. | All Managers to have a good understanding of these polices to be able to support staff fairly. Number of female and males employees requesting Hybrid guidance. | • 30th October 2021 • 31st January 2022 • 30th April 2022 • 30th August 2022 • 31st December 2022 | Bob Champion Interim Director of Workforce Karen Carter Head of Human Resources | EDI Group/EDI Team/AWE network |  | Workforce Data on number of staff requesting/granted Hybrid working solutions. | Green/Amber
3.2 | To ensure that women on Maternity leave are welcomed back and given the relevant training required and given time off for relevant appointments and to be able to have access to updates e.g. policies | All Managers to have a good understanding of these polices to be able to support staff fairly. | • 30th October 2021 • 31st January 2022 • 30th April 2022 • 30th August 2022 • 31st December 2022 | Bob Champion Interim Director of Workforce Karen Carter Head of Human Resources, Ali Lowe Head of OD | EDI Group/EDI Team/AWE network |  | OD Training stats on number of employees being offered 'Return to Work Induction' Training. | Green/Amber
Key Objective 4: Supporting Female Employees - Health, Wellbeing and retention
Ref. | Objective/Deliverable | KPI (if relevant) | Due Date | Owner | Driven through Working Group/Task & Finish Group | Location of related action plans | Comments/Update: | Delivery Confidence | Evidence Provided of completion | Evidence Assurance Provided to Committee | [36 empty] | A
4.2 | To ensure managers are aware of policies around menopause/uniform and women's health related issues are understood by all managers. | Develop relevant training for all managers. This should be made compulsory to help address any health challenges faced by women. | • 30th October 2021 • 31st January 2022 • 30th April 2022 • 30th August 2022 • 31st December 2022 | Ali Lowe Head of OD Jill Page Leadership Development & OD Manager, Rob Dimsdale, Well-being Manager | EDI Group/EDI Team/AWE network |  | MPT compliance. | Green/Amber

## Owners names
Owners | Job title | Indicators
Ali Lowe | Head of OD | 2 & 4
Amanda Marsh | Senior EDI HR lead - EDI team
Amy Antoni | Deputy Head of Resourcing | 2
Andree Weymouth | Workforce Planning & Information Manager and ESR Lead | 1
Barbara Shreeve/ Caroline Nwadu/ Emma Crawford | AWE Chairs | 2
Bob champion | Interim Director of Workforce | 1,2,3
Emma De Carteret | Head of Governance | 1 & 2
Helen Adams | Head of Resourcing | 1 & 2
Jill Page | Leadership Development & OD Manager | 2 & 4
Julie Hollings | Director of Communications and Engagement | 1
Karen Carter | Head of Human Resources | 3
Navrita Atwal | EDI Manager - EDI Team
Nicky Parry | EDI Administrator
Nikki Irons | PTS General Manager | 1
Paul Marshall | Deputy Chief Operating Officer (Ambulance Operations Centres and Community Response) | 1 & 2
Rob Dimsdale | Wellbeing Manager | 4
Rowena Welsford | Assoicate Director of Workforce | 1 & 2
Sonya Bhania | EDI Advisor
Sudha Pavanakumar | Deputy Director of Workforce | 2 & 3