## WRES Action plan
WORKFORCE RACE EQUALITY STANDARD 2022-2023 |  | Key objectives: | [5 empty] | Weekly RAG | Interdependencies |  | Barriers to Delivery | Mitigations
Overall Ambition/vision: |  | Key Objective 1: Percentage of staff in each of the AfC Bands 1-9 and VSM (including executive Board members) compared with the percentage of staff in the overall workforce. | [5 empty] | Green/Amber
|  | Key Objective 2 : Relative likelihood of white applicants being appointed from shortlisting across all posts compared to BME applicants. | [5 empty] | Green/Amber
|  | Key Objective 3 : Relative likelihood of BME staff entering the formal disciplinary process compared to white staff. | [5 empty] | Green/Amber
|  | Key Objective 4 : Relative likelihood of white staff accessing non-mandatory training and continuous professional development (CPD) compared to BME staff. I) To reduce the likelihood from 1.13 to 0.97 | [5 empty] | Green/Amber
|  | Key Objective 5 : Percentage of BME staff experiencing harassment, bullying or abuse from patients, relatives or public in the last 12 months. I) To reduce percentage from 34.3% to 31% | [5 empty] | Green/Amber
|  | Key Objective 6 : Percentage of BME staff experiencing harassment, bullying or abuse from staff over the last 12 months. I) To reduce from 38.5% to 34% | [5 empty] | Green/Amber
|  | Key Objective 7 : Percentage of BME staff believing that their trust provides equal opportunities for career progression or promotion | [5 empty] | Green/Amber
|  | Key Objective 8 : Percentage of BME staff personally experiencing discrimination at work from a manager/team leader or other colleagues. I) To reduce discrimination from 34.1% to 32% | [5 empty] | Green/Amber
|  | Key Objective 9 : Percentage difference between the organisations’ Board membership and its overall workforce disaggregated: A) By voting membership of the Board. B) By executive membership of the Board. | [5 empty] | Green/Amber
SRO | Director of Strategy, Education and Culture | Overall Workstream: EEAST has signed up to the Anti Racism charter led by Director of Strategy, Education and Culture and the Union. Objectives and Actions for this charter will support the WRES action plan. | [5 empty] | Green/Amber
Senior Management Support | Senior Programmes Lead Up to End of September 2022 From October 2022 Head of Culture & Inclusivity | Description of Engagement/ Comm's to staff:
Committee Reported to: | People Committee | Frequency of reporting: | Annually
Governance Group: | Equality, Diversity and Inclusion Group | Frequency of reporting: | Quarterly
Key Objective 1: Percentage of staff in each of the AfC Bands 1-9 and VSM (including executive Board members) compared with the percentage of staff in the overall workforce.
Ref. | Deliverable | KPI (if relevant) | Due Date | Owner | Driven through Working Group/Task & Finish Group | Location of related action plans | Comments/Update: | Delivery Confidence | Evidence Provided of completion | Evidence Assurance Provided to Committee
1.1 | EEAST will continue to encourage all employees to update their information on ESR. | Work will continue to be monitored throughout this reporting year. | 31/3/2023 | Equality, Diversity, and Inclusion Team | EDI Group |  |  | Green/Amber
1.2 | Minority Ethnic Recruitment & Retention Task & Finish Group to identify appropriate geographic targets to increase our BME workforce through specific recruitment campaigns. | This is being monitored through the workstream lead by Director of Business and Partnership. | 2023-03-31 | Director of Business and Partnership | Minority Ethnic Recruitment & Retention Task & Finish Group |  |  | Green/Amber
Key Objective 2 : Relative likelihood of white applicants being appointed from shortlisting across all posts compared to BME applicants.
Ref. | Deliverable | KPI (if relevant) | Due Date | Owner | Driven through Working Group/Task & Finish Group | Location of related action plans | Comments/Update: | Delivery Confidence | Evidence Provided of completion | Evidence Assurance Provided to Committee
2.1 | EEAST will continue to monitor this. | Work will continue to be monitored throughout this reporting year. | 31/3/2023 | Equality, Diversity, and Inclusion Team | EDI Group |  |  | Green/Amber
Key Objective 3 : Relative likelihood of BME staff entering the formal disciplinary process compared to white staff.
Ref. | Deliverable | KPI (if relevant) | Due Date | Owner | Driven through Working Group/Task & Finish Group | Location of related action plans | Comments/Update: | Delivery Confidence | Evidence Provided of completion | Evidence Assurance Provided to Committee
3.1 | Cultural Ambassador's are now in place at EEAST. EEAST will continue to monitor this. | Work will continue to be monitored throughout this reporting year. | 31/3/2023 | Equality, Diversity, and Inclusion Team | EDI Group |  |  | Green/Amber
Green/Amber
Key Objective 4 : Relative likelihood of white staff accessing non-mandatory training and continuous professional development (CPD) compared to BME staff. I) To reduce the likelihood from 1.13 to 0.97
Ref. | Deliverable | KPI (if relevant) | Due Date | Owner | Driven through Working Group/Task & Finish Group | Location of related action plans | Comments/Update: | Delivery Confidence | Evidence Provided of completion | Evidence Assurance Provided to Committee
4.1 | Legal Framework Training: to explore the law around discrimination, harassment & victimisation. "EDI - Making the mix work". Delegates will know the part they play in promoting a diverse & inclusive & safe working environment by the end of the session. Initially for staff at Pay Band 8a & above. Pilot session was held in May and delivered by Browne Jacobson LLP. | I) To reduce the likelihood of white staff from access non-mandatory training from 1.13 to 0.97 | 2023-03-31 | Head of Human Resources | EDI Group |  |  | Green/Amber
4.2 | Clinical & Professional Development team to draft NTK articles promoting non-mandatory training and send out information to BME network to bring it to their attention. Attend BME network to discuss how to apply for training, CPD etc. | I) To reduce the likelihood of white staff from access non-mandatory training from 1.13 to 0.97 | Commence 1/11/22 to conclude 31/03/23 | Clinical Lead for Education & Clinical Practice | EDI Group |  |  | Green/Amber
4.3 | Prompting & seeking applicants from the BME network for: Positive Action Programme in partnership with Norfolk & Waveney health Care Partnership | I) To reduce the likelihood of white staff from access non-mandatory training from 1.13 to 0.97 | Commences October 2022 | Leadership Development & OD Manager BME Network Chair | EDI Group |  |  | Green/Amber
4.4 | Prompting & seeking applicants (Bands 2-4) for the Inclusive Career Development Programme. For Herts and West Essex area staff. Application deadline 31/7/22 | I) To reduce the likelihood of white staff from access non-mandatory training from 1.13 to 0.97 | Commences September 2022 | Leadership Development & OD Manager (EEAST in partnership with Herts & West Essex ICS) | EDI Group |  |  | Green/Amber
Key Objective 5 : Percentage of BME staff experiencing harassment, bullying or abuse from patients, relatives or public in the last 12 months. I) To reduce percentage from 34.3% to 31%
Ref. | Deliverable | KPI (if relevant) | Due Date | Owner | Driven through Working Group/Task & Finish Group | Location of related action plans | Comments/Update: | Delivery Confidence | Evidence Provided of completion | Evidence Assurance Provided to Committee
5.1 | AACE #WorkWithoutFear national campaign. Highlighting & reducing violence, aggression & abuse directed at NHS Ambulance Staff. Posters, video's, social media and personal experiences to raise awareness. To be used by communications partners from the Ambulance Trusts. | To Reduce BME staff from experiencing harassment, bullying & abuse from:- Patients, relatives or public from 34.3% to 31% | 31/3/2023 | Health, Safety & Security Manager Director of Communications & Engagement | EDI Group |  |  | Green/Amber
Key Objective 6 : Percentage of BME staff experiencing harassment, bullying or abuse from staff over the last 12 months. I) To reduce from 38.5% to 34%
Ref. | Deliverable | KPI (if relevant) | Due Date | Owner | Driven through Working Group/Task & Finish Group | Location of related action plans | Comments/Update: | Delivery Confidence | Evidence Provided of completion | Evidence Assurance Provided to Committee
6.1 | Legal Framework Training: to explore the law around discrimination, harassment & victimisation. "EDI - Making the mix work". Delegates will know the part they play in promoting a diverse & inclusive & safe working environment by the end of the session. Initially for staff at Pay Band 8a & above. Pilot session was held in May and delivered by Browne Jacobson LLP. | To Reduce BME staff from experiencing harassment, bullying & abuse from 38.5% to 34% | 2023-03-31 | Head of Human Resources | EDI Group |  |  | Green/Amber
6.2 | Explore the possible development of a micro-aggression reporting portal. To enable people to anonymously report this & a platform to collate it. In partnership with Norfolk and Waveney CCG. | To Reduce BME staff from experiencing harassment, bullying & abuse from 38.5% to 34% | 31/3/2023 | Freedom to Speak Up Guardian (FTSU) Director of Strategy, Education and Culture Equality, Diversity, and Inclusion Team | EDI Group |  |  | Green/Amber
6.3 | To actively promote the Speak Up, Speak Out, Stop it campaign on NtK. FTSU team are scheduling in station visits. EDI Leads reference FTSU this at every network meeting & FTSU representative attends network meetings. FTSU have monthly meetings with each Head of Service to identify any issues or support required for staff. Consider FTSU producing NtK article to encourage staff to report incidents i.e. encouraging men to report harassment. | To Reduce BME staff from experiencing harassment, bullying & abuse from 38.5% to 34% | 31/3/2023 | Freedom to Speak Up Guardian (FTSU) Director of Communications and Engagement Equality, Diversity, and Inclusion Team | EDI Group |  |  | Green/Amber
Key Objective 7 : Percentage of BME staff believing that their trust provides equal opportunities for career progression or promotion
Ref. | Deliverable | KPI (if relevant) | Due Date | Owner | Driven through Working Group/Task & Finish Group | Location of related action plans | Comments/Update: | Delivery Confidence | Evidence Provided of completion | Evidence Assurance Provided to Committee
7.1 | Objectives in Indicator 4 will contribute to this indicator & also the project outside of the Action Plan (see 1.2). EEAST has engaged an external consultancy (McKinsey) to undertake comprehensive surveying of BME staff. Project being scoped at the moment. | Work will continue to be monitored throughout this reporting year. | 31/3/2023 | Equality, Diversity, and Inclusion Team | EDI Group |  |  | Green/Amber
Key Objective 8 : Percentage of BME staff personally experiencing discrimination at work from a manager/team leader or other colleagues. I) To reduce discrimination from 34.1% to 32%
Ref. | Deliverable | KPI (if relevant) | Due Date | Owner | Driven through Working Group/Task & Finish Group | Location of related action plans | Comments/Update: | Delivery Confidence | Evidence Provided of completion | Evidence Assurance Provided to Committee
8.1 | Legal Framework Training: to explore the law around discrimination, harassment & victimisation. "EDI - Making the mix work". Delegates will know the part they play in promoting a diverse & inclusive & safe working environment by the end of the session. Initially for staff at Pay Band 8a & above. Pilot session was held in May and delivered by Browne Jacobson LLP. | To reduce BME staff from experiencing discrimination from 34.1% to 32% | 2023-03-31 | Head of Human Resources | EDI Group |  |  | Green/Amber
8.2 | Continue to roll out the Manager’s Passport Training Programme. All Managers to complete the 5 Mandated Managers Training Module: Dignity at work, Disability Awareness, Disciplinary, Policy, Grievance Training & Safeguarding - Allegations against staff. 50% of managers to have successfully completed the training package on Evolve by 31/7/2022. | To reduce BME staff from experiencing discrimination from 34.1% to 32% | 2023-03-31 | Director of Strategy, Education and Culture | EHRC Action |  |  | Green/Amber
Green/Amber
Key Objective 9 : Percentage difference between the organisations’ Board membership and its overall workforce disaggregated: A) By voting membership of the Board. B) By executive membership of the Board.
Ref. | Deliverable | KPI (if relevant) | Due Date | Owner | Driven through Working Group/Task & Finish Group | Location of related action plans | Comments/Update: | Delivery Confidence | Evidence Provided of completion | Evidence Assurance Provided to Committee
9.1 | Board and Executive Directors membership will continue to be updated quarterly through the completion information on ESR and other approved proformas. | Work will continue to be monitored throughout this reporting year. | 31/3/2023 | Equality, Diversity, and Inclusion Team | EDI Group |  |  | Green/Amber

## NHS WRES Indicators
Indicator number | WRES INDICATORS
1 | Percentage of staff in each of the AfC Bands 1-9 and VSM (including executive Board members) compared with the percentage of staff in the overall workforce.
2 | Relative likelihood of white applicants being appointed from shortlisting across all posts compared to BME applicants.
3 | Relative likelihood of BME staff entering the formal disciplinary process compared to white staff.
4 | Relative likelihood of white staff accessing non-mandatory training and continuous professional development (CPD) compared to BME staff.
5 | Percentage of staff experiencing harassment, bullying or abuse from patients, relatives or public in the last 12 months
6 | Percentage of staff experiencing harassment, bullying or abuse from staff over the last 12 months
7 | Percentage of staff believing that their trust provides equal opportunities for career progression or promotion
8 | Percentage of staff personally experiencing discrimination at work from a manager/team leader or other colleagues.
9 | Percentage of BME board Membership